## Sprint 1
Sprint Review Protocol
Sprint No: |  | 1
Date & Time |  | 2023-11-06
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Inno Erklärung
0 | Meeting FH | 10 | 10 | 0 | 1 |  | Kennenlernen, ganz grobe Ideensammlung
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Diary-Meeting ohne Petz
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Diary-Meeting mit Petz
0 | Meeting FH | 10 | 10 | 0 | 1 |  | Idea-Brainstorming mit Petz
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Organisatorisches, Sprintbesprechung
0 | Unity Programmer Path 1/2 | 16 | 16 | 0 | 1 |  | Alle außer Johann
0 | High Concept | 4 | 4 | 0 | 1 |  | Johann
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
0 |  |  |  | 0
16 |  | 60 | 60 | 0 | 8 | 0
60

## Sprint 2
Sprint Review Protocol
Sprint No: |  | 2
Date & Time |  | 2023-11-21
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Sprint 1 Review
0 | Meeting FH | 5 | 5 | 0 | 1 |  | General Art Design/Direction
0 | Meeting Discord | 10 | 10 | 0 | 1 |  | Organisatorisches, Sprintbesprechung
0 | Unity Programmer Path | 10 | 10 | 0 | 1 |  | Alle
0 | High Concept | 2 | 2 | 0 |  | 1 | Johann: Noch nicht fertig
0 | Gamedesign sketches | 3 | 3 | 0 | 1 |  | Johann: Krita is müll
0 | Design Main Character | 6 | 6 | 0 |  | 1 | Tobi + Vincent: mit nix zufrieden
0 | Projekt aufsetzen | 6 | 6 | 0 |  | 1 | Flo + Domi: Unity Cloud / Git ?
0
0
0
0
0
8 |  | 47 | 47 | 0 | 5 | 3
60

## Sprint 3
Sprint Review Protocol
Sprint No: |  | 3
Date & Time |  | 2023-12-05
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Alle: Sprint 2 Review
0 | Meeting Discord | 20 | 20 | 0 | 1 |  | Alle: Arbeitspackete definieren
0 | Meeting Discord | 10 | 10 | 0 | 1 |  | Alle: Organisatorisches, Sprintbesprechung
0 | Meeting Discord | 4 | 4 | 0 | 1 |  | Johann, Vincent: game-design / artstyle
0 | Meeting Discord | 6 | 6 | 0 | 1 |  | Vincent, Tobi: tilemap-design
58 | Design: Theme Floor A | 2 | 2 | 0 | 1 |  | Vincent, Tobi
60 | Sketch: Ground Floor A | 16 | 10 | -6 | 1 |  | Vincent, Tobi
122 | Art: Ground Floor A | 4 | 8 | 4 | 1 |  | Vincent
167 | High Concept | 3 | 3 | 0 | 1 |  | Johann
4 | Programming: Player Basic Movement | 2 | 2 | 0 | 1 |  | Dominik, Florian
5 | Programming: Entity spawn | 8 | 8 | 0 | 1 |  | Dominik, Florian
6 | Programming: Player Health (Code / UI) | 4 | 3 | -1 | 1 |  | Florian
21 | Programming: Player dash | 4 | 3 | -1 |  | 1 | Dominik
0
0
13 |  | 88 | 84 | -4 | 12 | 1
60

## Sprint 4
Sprint Review Protocol
Sprint No: |  | 4
Date & Time |  | 2023-12-19
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Alle: Sprint 3 Review
0 | Meeting Discord | 10 | 10 | 0 | 1 |  | Alle: Organisatorisches, Sprintbesprechung
0 | Meeting Discord | 2 | 2 | 0 | 1 |  | Dominik + Florian: Git Project
0 | Meeting Discord | 4 | 4 | 0 | 1 |  | Vincent + Tobi: Artstyle simpler gemacht -> Perspektive angepasst
0 | Meeting Discord | 6 | 6 | 0 | 1 |  | Vincent + Tobi: Tilemap überarbeiten, Art scaling
14 | Programming: Attack hitbox trigger | 8 | 6 | -2 | 1 |  | Dominik + Florian: Layering
15 | Programming: Projectile Behavior | 2 | 3 | 1 | 1 |  | Dominik: Mouse Position auslesen
16 | Programming: AOE Behavior | 4 | 3 | -1 | 1 |  | Dominik
21 | Programming: Player dash | 1 | 1 | 0 | 1 |  | Dominik
31 | Programming: Enemy Spawner | 4 | 3 | -1 | 1 |  | Florian
36 | Programming: Enemy Collisions | 2 | 2 | 0 | 1 |  | Florian
41 | Sketch: Trojaner | 8 | 7 | -1 | 1 |  | Tobi: Tablet einrichten
43 | Sketch: Virus | 8 | 6 | -2 | 1 |  | Vincent
144 | Design: Trojaner | 2 | 2 | 0 | 1 |  | Johann
145 | Design: Spyware | 2 | 2 | 0 | 1 |  | Johann
146 | Design: Virus | 2 | 2 | 0 | 1 |  | Johann
147 | Design: Ransomware | 2 | 2 | 0 | 1 |  | Johann
17 |  | 72 | 66 | -6 | 17 | 0
60

## Sprint 5
Sprint Review Protocol
Sprint No: |  | 5
Date & Time |  | 2024-01-16
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 5 | 5 | 0 | 1 |  | Alle: Sprint 4 Review
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Alle: Organisatorisches, Sprintbesprechung
0 | Meeting Discord | 2 | 2 | 0 | 1 |  | Vincent + Johann: Gegnerdesign
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Alle: Health System/Healthbar Diskussion
0 | Meeting Discord | 2 | 2 | 0 | 1 |  | Vincent + Tobi: Healthbar Diskussion + Sketching
0 | Meeting Discord | 4 | 4 | 0 | 1 |  | Vincent + Johann: Räume feedback
0 | Meeting Discord | 2 | 2 | 0 | 1 |  | Dominik + Tobi: Healthbar in Unity
7 | Programming: Player Weapons Fire | 8 | 10 | 2 | 1 |  | Dominik + Florian: Neue Design Ideen
8 | Programming: Player Weapons Reload | 2 | 2 | 0 | 1 |  | Dominik
11 | Programming: Enemy Movement | 4 | 5 | 1 |  | 0 | Florian: Unity Version conflict
12 | Programming: Enemy Health (Code / UI) | 2 | 2 | 0 | 1 |  | Florian
13 | Programming: Enemy Attacks | 4 | 3 | -1 | 1 |  | Dominik
152 | Design: Räume planen | 20 | 6 | -14 |  | 0 | Johann: Work in progress
155 | Design: Inventory/Items planen | 8 | 2 | -6 |  | 0 | Johann: Work in progress
37 | Sketch: Main Character | 8 | 6 | -2 |  | 0 | Vincent + Tobi: Work in progress
49 | Sketch: Healthbar | 2 | 4 | 2 | 1 |  | Tobi: Design Umentscheidung
61 | Sketch: Walls Floor A | 4 | 2 | -2 |  | 0 | Vincent + Tobi: Work in progress
78 | Sketch: Bit -> Bat | 4 | 2 | -2 |  | 0 | Vincent
0
18 |  | 91 | 69 | -22 | 12 | 6
60

## Sprint 6
Sprint Review Protocol
Sprint No: |  | 6
Date & Time |  | 2024-01-29
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
0 | Meeting Zoom | 10 | 10 | 0 | 1 |  | Alle: Sprint 5 Review & Presentation
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Alle: Organisatorisches, Sprintbesprechung
0 | Meeting Discord | 10 | 10 | 0 | 1 |  | Alle: Merge on Dev, Enemy Behavior Diskussion
0 | Meeting Discord | 20 | 20 | 0 | 1 |  | Alle: Presentation Preparation
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Alle: Game Concept (Serious Game)
0 | Meeting Discord | 5 | 5 | 0 | 1 |  | Alle: Sprint 6 Review + Video
0 | PowerPoint & Video | 2 | 2 | 0 | 1 |  | Johann
32 | Programming: Wall, Ground, Hole tiles | 4 | 1 | -3 |  | 1 | Dominik: Texture Problems
26 | Programming: Health packs | 2 | 2 | 0 | 1 |  | Florian
11 | Programming: Enemy Movement | 4 | 1 | -3 | 1 |  | Florian: (Sprint 5)
152 | Design: Räume planen | 20 | 0 | -20 |  | 1 | Johann: Work in progress
155 | Design: Inventory/Items planen | 8 | 0 | -8 |  | 1 | Johann: Work in progress
37 | Sketch: Main Character | 8 | 2 | -6 | 1 |  | Vincent + Tobi: (Sprint 5)
61 | Sketch: Walls Floor A | 4 | 1 | -3 | 1 |  | Vincent + Tobi: (Sprint 5)
78 | Sketch: Bit -> Bat | 4 | 2 | -2 | 1 |  | Vincent
123 | Art: Walls Floor A | 4 | 4 | 0 | 1 |  | Dominik + Tobi: Wall Texture Unity integration
16 |  | 115 | 70 | -45 | 13 | 3
60

## Sprint 7
Sprint Review Protocol
Sprint No: |  | 7
Date & Time |  | 2024-04-02
Group Number |  | 18
Participant 1 |  | Bernhart-Straberger Vincent
Participant 2 |  | Kastl Tobias
Participant 3 |  | Lang Johann
Participant 4 |  | Neuwirth Dominik
Participant 5 |  | Poppinger Florian
Mentor |  | Petz Markus
Req ID | short description [opt] | Estimate [h] | Real Efort [h] | Delta [h] | Passed | failed | remarks
| Meeting Discord | 0 | 10 | 10 |  |  | Alle: Arbeitsaufteilung erster Sprint
| Meeting Discord | 0 | 10 | 10 |  |  | Alle: Game Design Document
| Meeting Discord | 0 | 10 | 10 |  |  | Alle: Sprint Review
0
0 | Demo Graphics | 0 | 2 | 2 | 1 |  | Johann
0 | Main Character Update | 0 | 1 | 1 | 1 |  | Vincent
0 | Basic level setup | 0 | 1 | 1 | 1 |  | Tobias
| Basic level setup |  | 1 | 1 |  |  | Florian
0 | Character move on Tiles | 0 | 2 | 2 | 1 |  | Florian
0 | Character pick up trash | 0 | 1 | 1 | 1 |  | Dominik
0 | Drag and drop UI Element | 0 | 1 | 1 | 1 |  | Vincent
0 | Copy UI element/prefab | 0 | 2 | 2 | 1 |  | Dominik
0 | Call character Funktion from UI | 0 | 1 | 1 | 1 |  | Johann
0 | Sketch of main view/UI | 0 | 2 | 2 | 1 |  | Tobias
| Sketch of main view/UI |  | 1 | 1 |  |  | Vincent
9 |  | 0 | 45 | 45 | 9 | 0
60